## Sheet1
Phase | Task | Deadline | Notes
Preparation | Finalize thesis topic | 15/12/2024 | Confirm with professor
Literature Review | Review background literature | 25/12/2024 | Collect, read, and organize references.
Methodology Chapter | Write Methodology chapter (covering BAYWATCH phases) | 2025-07-01 | Include the steps and phases in the BAYWATCH method.
Artificial Data Creation | Create artificial data and apply FFT and Autocorrelation | 13/01/2025 | Generate data and validate it using FFT and Autocorrelation analysis.
Experiment Chapter | Write Experiment chapter | 31/01/2025 | Document experiment design and initial results.
Data Analysis | Work on real data (visit URLs, preprocess, etc.) | 2025-07-02 | Focus on extracting meaningful patterns and insights from real data.
Artificial Data Expansion | Expand artificial dataset | 17/02/2025 | Simulate more complex scenarios or scale data for broader experiments.
Thesis Writing | Write Chapters 1, 2, 7, and 8 | 2025-07-03 | Focus on Introduction, Background, Conclusion, and Future Work chapters.
last check with Professor | all chapters | 2025-07-03 | review all chapters!
Submission | Submit finalized thesis | 14/03/2025 | Ensure all proofreading and formatting are complete before submission.